======================================================================

DIGITALLY DEFINED

DOCUMENT 015

SCHEDULING STANDARDS

DOCUMENT ID:

DD-015

VERSION:

1.0

STATUS:

FROZEN

DOCUMENT OWNER:

Digitally Defined

======================================================================

PURPOSE

The Scheduling Standards establish the procedures for planning,

coordinating, assigning, tracking, and completing all projects within

the Digitally Defined Builder Program.

The objective is to maximize technician efficiency, maintain builder

deadlines, eliminate scheduling conflicts, and provide predictable

project execution.

======================================================================

SCOPE

This document applies to:

• Builder Projects

• Model Homes

• Homeowner Upgrades

• Warranty Work

• Service Calls

• Installation Teams

• Project Management

======================================================================

SCHEDULING OBJECTIVES

Every schedule shall:

• Meet builder deadlines

• Maximize technician productivity

• Minimize travel time

• Eliminate scheduling conflicts

• Maintain installation quality

• Improve customer communication

======================================================================

PROJECT STATUS

Pending

Project has not been scheduled.

--------------------------------------------------

Scheduled

Project has been assigned.

--------------------------------------------------

Ready

Materials available.

Builder released.

Ready for installation.

--------------------------------------------------

In Progress

Installation has started.

--------------------------------------------------

Inspection Required

Installation complete.

Awaiting Quality Control.

--------------------------------------------------

Complete

Project closed.

Documentation complete.

--------------------------------------------------

Warranty

Project returned for service.

======================================================================

SCHEDULING WORKFLOW

Builder Release

↓

Verify Scope

↓

Verify Materials

↓

Assign Technician

↓

Schedule Installation

↓

Complete Installation

↓

Quality Control

↓

Project Closeout

======================================================================

SCHEDULING REQUIREMENTS

Every scheduled project shall include:

• Builder Name

• Community

• Lot Number

• Floor Plan

• Installation Type

• Assigned Technician

• Scheduled Date

• Estimated Labor Hours

• Required Materials

• Required Products

======================================================================

INSTALLATION PHASES

Phase 1

Prewire

--------------------------------------------------

Phase 2

Trim

--------------------------------------------------

Phase 3

Equipment Installation

--------------------------------------------------

Phase 4

Programming

--------------------------------------------------

Phase 5

Quality Control

--------------------------------------------------

Phase 6

Project Closeout

======================================================================

TECHNICIAN ASSIGNMENT

Scheduling shall consider:

• Skill Level

• Certifications

• Workload

• Project Complexity

• Geographic Location

• Previous Builder Experience

======================================================================

SCHEDULING PRIORITIES

Priority 1

Builder Deadline

--------------------------------------------------

Priority 2

Customer Commitment

--------------------------------------------------

Priority 3

Material Availability

--------------------------------------------------

Priority 4

Technician Availability

--------------------------------------------------

Priority 5

Travel Efficiency

======================================================================

CHANGE MANAGEMENT

Schedule changes shall be documented for:

• Builder Delays

• Material Delays

• Weather

• Customer Requests

• Technician Availability

• Scope Changes

======================================================================

DAILY PRODUCTION MEETING

The Operations Manager shall verify:

• Today's Schedule

• Material Readiness

• Technician Assignments

• Vehicle Readiness

• Open Issues

• Safety Concerns

• Quality Concerns

======================================================================

PROJECT CLOSEOUT REQUIREMENTS

Before closing a project:

• Installation Complete

• Quality Control Passed

• Photos Uploaded

• Documentation Complete

• Builder Sign-Off (if required)

• Customer Orientation Completed (if applicable)

======================================================================

SCHEDULING RULES

1.

No project shall be scheduled until all required

materials are available or confirmed.

--------------------------------------------------

2.

Every project shall have one assigned lead technician.

--------------------------------------------------

3.

Schedule changes shall be documented immediately.

--------------------------------------------------

4.

Projects shall follow the approved installation phases.

--------------------------------------------------

5.

Quality Control shall be completed before project

closeout.

--------------------------------------------------

6.

Completed projects shall be closed within one business

day after final approval.

======================================================================

KEY PERFORMANCE INDICATORS

On-Time Completion

Target:

98%

--------------------------------------------------

Schedule Accuracy

Target:

95%

--------------------------------------------------

Average Project Delay

Target:

Less than 1 Day

--------------------------------------------------

Technician Utilization

Target:

85%–90%

--------------------------------------------------

Quality Control Pass Rate

Target:

95% Minimum

======================================================================

REFERENCED DOCUMENTS

DD-003 Labor Library

DD-004 Assembly Library

DD-011 Installation Standards

DD-012 Quality Control Standards

DD-013 Purchasing Standards

DD-014 Inventory Standards

DD-016 Warranty Standards

======================================================================

REVISION HISTORY

Version 1.0

Initial Release

======================================================================

END OF DOCUMENT

DD-015

======================================================================