======================================================================

DIGITALLY DEFINED

QUALITY ASSURANCE STANDARDS LIBRARY

STANDARD ID

DD-0613

--------------------------------------------------

STANDARD CLASSIFICATION CODE

QA-DPL-001

--------------------------------------------------

STANDARD NAME

Deficiency & Punch List

Management Standard

VERSION

1.0

STATUS

FROZEN

======================================================================

STANDARD METADATA

Standard Category

Quality Assurance Standards

--------------------------------------------------

Standard Type

Deficiency Identification,

Tracking & Resolution

--------------------------------------------------

Difficulty Level

3 of 5

--------------------------------------------------

Required Crew

Lead Technician

Project Manager

Quality Inspector (As Required)

--------------------------------------------------

Estimated Labor

Automatically Generated

Referenced from LAB Library

--------------------------------------------------

Required Skill Level

Level-2

--------------------------------------------------

Dependencies

DD-058 Assembly Standards Library

DD-060 Service Standards Library

DD-0611 Quality Inspection &

Verification Standard

DD-0612 Photo Documentation Standard

QC Library

Digital Project Record

Project Drawings

======================================================================

PURPOSE

The Deficiency & Punch List Management Standard

establishes the Digitally Defined procedures for

identifying, documenting, assigning, correcting,

verifying, and closing project deficiencies.

The objective is to ensure all deficiencies are

resolved consistently before project turnover while

maintaining accountability, documentation,

communication, and measurable quality performance.

======================================================================

QUALITY OBJECTIVES

Identify deficiencies early.

--------------------------------------------------

Prevent project delays.

--------------------------------------------------

Maintain accountability.

--------------------------------------------------

Reduce rework.

--------------------------------------------------

Ensure complete project turnover.

--------------------------------------------------

Maintain accurate project records.

======================================================================

STANDARD APPLICATIONS

Required For

• New Construction

• Renovation Projects

• Service Projects

• Equipment Upgrades

• Commissioning

• Final Quality Inspections

• Customer Walkthroughs

======================================================================

DEFICIENCY IDENTIFICATION

Sources

□ Internal Inspection

□ Project Manager Review

□ Technician Self-Inspection

□ Customer Walkthrough

□ Engineer Review

□ Manufacturer Inspection

□ Service Inspection

--------------------------------------------------

Every identified issue shall be documented.

======================================================================

DEFICIENCY CLASSIFICATION

LEVEL 1

Critical

Examples

• Safety hazards

• System inoperable

• Life safety issue

• Code violation

Required Response

Immediate

--------------------------------------------------

LEVEL 2

Major

Examples

• System functionality affected

• Incorrect installation

• Missing equipment

• Failed testing

Required Response

Before customer acceptance

--------------------------------------------------

LEVEL 3

Minor

Examples

• Cosmetic defects

• Label corrections

• Minor adjustments

Required Response

Before project closeout

--------------------------------------------------

LEVEL 4

Observation

Examples

• Improvement recommendation

• Best practice suggestion

No corrective action required unless approved.

======================================================================

DEFICIENCY RECORD

Every Deficiency Shall Include

□ Unique deficiency number

□ Date identified

□ Project number

□ Room / location

□ Equipment affected

□ Description

□ Severity level

□ Assigned technician

□ Target completion date

□ Supporting photographs

======================================================================

ASSIGNMENT PROCEDURE

Assign

□ Responsible technician

□ Responsible department

□ Required materials

□ Estimated labor

□ Completion deadline

--------------------------------------------------

Responsibility shall be acknowledged before work

begins.

======================================================================

CORRECTIVE ACTION

Perform

□ Root cause review

□ Correct installation

□ Replace equipment

□ Reprogram system

□ Update documentation

□ Retest system

--------------------------------------------------

Corrective work shall follow all applicable

Digitally Defined standards.

======================================================================

REINSPECTION

After Correction

Verify

□ Deficiency corrected

□ System operational

□ Documentation updated

□ Photos captured

□ Related deficiencies resolved

□ Quality approved

======================================================================

CUSTOMER COMMUNICATION

Inform Customer When

□ Major deficiencies identified

□ Schedule affected

□ Additional work required

□ Change order required

□ Customer action required

--------------------------------------------------

Maintain communication until deficiency closure.

======================================================================

PUNCH LIST MANAGEMENT

Track

□ Open items

□ Assigned items

□ Completed items

□ Verified items

□ Closed items

--------------------------------------------------

Punch list shall remain current throughout the

project.

======================================================================

QUALITY CONTROL

Verify

□ All deficiencies documented

□ Photos complete

□ Assignments complete

□ Reinspection completed

□ Documentation updated

□ Closeout approved

======================================================================

DOCUMENTATION

Required

□ Deficiency Log

□ Punch List

□ Corrective Action Report

□ QC Photographs

□ Reinspection Report

□ Project Record Update

□ Digital Project Record Updated

======================================================================

PROJECT CLOSEOUT

Before Turnover

□ No open critical deficiencies

□ No open major deficiencies

□ Minor deficiencies resolved

□ Documentation complete

□ Quality approval received

□ Customer walkthrough complete

======================================================================

KEY PERFORMANCE INDICATORS (KPIs)

Deficiency Rate

--------------------------------------------------

Average Correction Time

--------------------------------------------------

Reinspection Pass Rate

--------------------------------------------------

Repeat Deficiency Rate

--------------------------------------------------

Project Rework Percentage

--------------------------------------------------

Quality Closure Rate

======================================================================

QUALITY RULES

1.

Every identified deficiency shall receive a unique

tracking number and documented corrective action.

--------------------------------------------------

2.

Critical deficiencies shall be corrected

immediately.

--------------------------------------------------

3.

Major deficiencies shall be resolved before

customer acceptance.

--------------------------------------------------

4.

Every corrected deficiency shall be re-inspected

before closure.

--------------------------------------------------

5.

Only approved Digitally Defined corrective

procedures shall be utilized.

--------------------------------------------------

6.

Every project shall achieve complete deficiency

closure before final project turnover unless

otherwise approved in writing by the customer.

======================================================================

COMMON ERRORS TO AVOID

• Undocumented deficiencies

• Missing photographs

• Poor deficiency descriptions

• No assigned ownership

• Closing deficiencies without verification

• Failure to update documentation

• Incomplete punch lists

======================================================================

REFERENCED LIBRARIES

DD-058 Assembly Standards Library

DD-060 Service Standards Library

DD-0611 Quality Inspection &

Verification Standard

DD-0612 Photo Documentation Standard

QC Library

LAB Library

Project Drawings

Digital Project Record

======================================================================

REVISION APPROVAL

Quality Manager Approval

______________________

Operations Approval

______________________

Effective Date

______________________

Supersedes Version

N/A

Change Summary

Initial Release

======================================================================

END OF STANDARD

DD-0613

======================================================================